## Sheet1
PROGRESS OF DISCOM AT A GLANCE AS ON 31.10.2012
Scheme |  | Total No. Of 11 KV Feeders | Survey of 11 KV feeders | Pole Transportation | Pole erection | 11 KV stringing (Km) | Installation of DTR | Replacement of bare cond. By AB cable | Total Meters to be installed
Phase I | Provision | 1209 | 1209 | 98120 | 98120 | 7483 | 9081 | 5795 | 225849
| Achievement | 658 | 1209 | 79165 | 68879 | 2848 | 2667 | 2213.5 | 90238
| % Achievement | 54% | 100% | 81% | 70% | 38% | 29% | 38% | 40%
Phase II | Provision | 1118 | 1118 | 150499 | 150499 | 6380 | 13357 | 4726 | 272730
| Achievement | 366 | 913 | 86512 | 69444 | 2525.97 | 1824 | 1207.6 | 63489
% Achievement |  | 32% | 82% | 57% | 46% | 40% | 14% | 26% | 23%
ADB | Provision | 171 | 171 | 26387 | 26387 | 1865 | 4316 | 718 | 10190
| Achievement | 126 | 171 | 24823 | 21472 | 2020.12 | 3218 | 718 | 10190
RGGVY/Departmental | Provision | 125 | 125 | 7795 | 7795 | 301.4 | 604 | 628.2 | 12000
| Achievement | 125 | 125 | 7795 | 8976 | 247.18 | 456 | 624.77 | 7573
Grand Total | Provision | 2642 | 2642 | 282801 | 282801 | 16029 | 27358 | 11403 | 520769
| Achievement | 1275 | 2418 | 198295 | 168771 | 7641.3 | 8165 | 4763.9 | 171490
% Achievement. |  | 48% | 92% | 70% | 60% | 48% | 30% | 42% | 33%

## Sheet2
INDORE REGION
FEEDER SEPARATION PROGRESS(FSP,RGGVY AND ADB)
S.N. | Name of Districts | Total Feeder to be separated | Villages to be benefitted | Feeder separated up to Sep.2012 | Target for Oct-12 | Achievement during Oct 1212 | Feeder separated upto Oct.2012 | No. of Village Benefited upto Oct 2012 | Target for Nov’12 | % Achievement | Likely Completion on month
1 | INDORE | 284 | 625 | 132 | 14 | 16 | 148 | 375 | 15 | 52% | Dec’12
2 | DHAR | 244 | 1337 | 189 | 10 | 16 | 205 | 637 | 10 | 84% | Dec’12
3 | BARWANI | 144 | 662 | 44 | 11 | 10 | 55 | 162 | 12 | 38% | Dec’12
4 | KHARGONE | 266 | 1156 | 81 | 25 | 19 | 55 | 152 | 26 | 21% | Dec’12
5 | KHANDWA | 135 | 705 | 46 | 7 | 9 | 100 | 235 | 8 | 74% | Dec’12
6 | BURHANPUR | 66 | 258 | 52 | 14 | 3 | 54 | 123 | 11 | 82% | Oct’12
7 | JHABUA | 52 | 752 | 13 | 3 | 3 | 16 | 90 | 4 | 31% | March’13
8 | ALIRAJPUR | 28 | 529 | 13 | 2 | 1 | 14 | 80 | 2 | 50% | March’13
Total |  | 1219 | 6024 | 570 | 86 | 77 | 647 | 1854 | 88 | 53%

## Sheet3
UJJAIN REGION
FEEDER SEPARATION PROGRESS(FSP,RGGVY AND ADB)
S.N. | Name of Districts | Total Feeder to be separated | Villages to be benefitted | Feeder separated upto SEP’ 2012 | Target for Oct’12 | Achievement during Oct’12 | Feeder separated upto Oct’2012 | No. of Village Benefited upto Aug-.2012 | Target for Nov’12 | % Achievement | Likely Completion on month
1 | UJJAIN | 335 | 1096 | 175 | 14 | 23 | 198 | 617 | 10 | 59% | March’13
2 | RATLAM | 202 | 1053 | 125 | 8 | 10 | 135 | 352 | 10 | 67% | Nov’12
3 | DEWAS | 221 | 1055 | 86 | 11 | 19 | 105 | 327 | 11 | 47% | March’13
4 | SHAHJAPUR | 273 | 1106 | 61 | 18 | 17 | 78 | 343 | 12 | 28% | March’13
5 | MANDSAUR | 234 | 906 | 53 | 15 | 18 | 71 | 271 | 14 | 30% | March’13
6 | NEEMUCH | 158 | 674 | 30 | 10 | 11 | 41 | 150 | 8 | 26% | March’13
|  | 1423 | 5890 | 530 | 76 | 78 | 628 | 2060 | 64 | 44%
Grand Total |  | 2642 | 11914 | 1100 | 162 | 175 | 1275 | 3914 | 152 | 48%

## Sheet4
Abstract of Charging status of feeder under Indore Commissionaire and Ujjain Commissionaire
Sr. No. | Name of District | No. of feeders completed Up to Oct.’ 12 | No. of Village completed Up to Oct.’ 12 | Charging Status of Feeders
|  |  |  | No. of Feeders charged for 20 Hrs | No. of Villages charged for 20 Hrs | No. of Feeders charged for 16 Hrs/14 Hrs | No. of Village Benefitted On 16 Hrs/14Hrs.
1 | INDORE | 148 | 375 | 84 | 210 | 64 | 165
2 | DHAR | 205 | 637 | 150 | 450 | 55 | 187
3 | KHANDWA | 55 | 152 | 32 | 82 | 23 | 70
4 | BURHANPUR | 55 | 162 | 30 | 88 | 25 | 74
5 | BARWANI | 54 | 123 | 26 | 28 | 28 | 95
6 | JHABUA | 16 | 90 | 5 | 31 | 11 | 59
7 | ALIRAJPUR | 14 | 80 | 7 | 39 | 7 | 41
8 | KHARGONE | 100 | 235 | 52 | 134 | 48 | 101
9 | Ujjain | 198 | 617 | 106 | 324 | 92 | 293
10 | Dewas | 105 | 327 | 34 | 118 | 71 | 209
11 | Mandsaur | 71 | 271 | 31 | 101 | 40 | 170
12 | Neemuch | 41 | 150 | 17 | 48 | 24 | 102
13 | Shajapur | 78 | 343 | 29 | 107 | 49 | 236
14 | Ratlam | 135 | 352 | 72 | 167 | 63 | 135
Total |  | 1275 | 3914 | 675 | 1927 | 600 | 1937